## 📋 Master Database
ESTIMATION PRESET DATABASE · v2.0
CORE | [6 empty] | DISCOVERABILITY |  |  |  | COMPLEXITY |  |  | SEQUENCING |  |  |  | EFFORT INTELLIGENCE |  |  | NOTES
ID | Category | Preset Name | Description | BE (h) | FE (h) | Total (h) | Platforms | Req. type | Keywords | User story tags | Project size fit | Integration count | Data volume | Phase | Requires | Blocks | Can parallel | AI assist | Risk | Research needed | Notes / Assumptions
P01 | Dev Environment | R&D — Contentful & Contentful Studio | Research spike on Contentful content modeling, Studio/Experiences constraints, and slice architecture. | 32 | 0 | 32 | Contentful | Research & Discovery | contentful, cms, studio, content modeling, spike | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Foundation |  | P14¦P15¦P16¦P17¦P18¦P19¦P20¦P21 | No | Low | Low | Yes | Findings gate all CMS implementation. Run before any Contentful build work.
P02 | Dev Environment | R&D — Epicor P21 API | Spike on P21 API capabilities, endpoint availability (pricing, inventory, orders, customers) and integration constraints. | 24 | 0 | 24 | P21 | Research & Discovery | P21, Epicor, ERP, API, endpoints, inventory, pricing, spike | Dev ops | Mid-market¦Enterprise | 1 | None | Foundation |  | P07¦P08¦P09¦P24 | No | Low | High | Yes | No custom P21 dev included. P21 must already expose required endpoints.
P03 | Dev Environment | R&D — Celigo | Spike on Celigo connector configuration, available adaptors, and flow patterns for P21/Shopify/Contentful. | 8 | 0 | 8 | Celigo | Research & Discovery | celigo, iPaaS, ETL, integration platform, flows, connectors, spike | Dev ops | Mid-market¦Enterprise | 1 | None | Foundation |  | P07¦P08¦P09¦P10 | No | Low | Medium | Yes | Celigo license and sandbox must be provisioned before spike.
P04 | Dev Environment | R&D — Klevu | Spike on Klevu indexing API, search relevance features, and faceting capabilities. | 6 | 0 | 6 | Klevu | Research & Discovery | klevu, search, indexing, faceting, relevance, spike | Dev ops | Mid-market¦Enterprise | 1 | None | Foundation |  | P11¦P12¦P13 | No | Low | Low | Yes | Klevu sandbox required. Subscription must cover 90k+ SKUs if applicable.
P05 | Dev Environment | R&D — PIM platform | Spike on PIM platform schema design, ingestion patterns, and integration with Shopify and Celigo. | 16 | 0 | 16 | PIM | Research & Discovery | PIM, product information, schema, ingestion, attributes, spike | Dev ops | Mid-market¦Enterprise | 1 | None | Foundation |  | P06¦P07¦P08 | No | Low | Medium | Yes | PIM must be selected and licensed before spike begins.
P06 | Dev Environment | R&D — Act-On | Spike on Act-On API, form submission endpoint, and lead capture integration patterns. | 4 | 0 | 4 | Act-On | Research & Discovery | act-on, marketing automation, lead gen, form submission, spike | Dev ops¦Marketing editor | SMB¦Mid-market¦Enterprise | 1 | None | Foundation |  | P22 | No | Low | Low | Yes | Act-On credentials required before spike.
P07 | Integration / Celigo | API gateway & environment setup | Establish composable architecture foundation: API gateway, environment scaffolding, and security configuration for all integration layers. | 24 | 12 | 36 | Shopify¦Celigo¦P21¦Vercel | Infrastructure | API gateway, environment setup, security, scaffolding, architecture, foundation | Dev ops | Mid-market¦Enterprise | 4 | None | Foundation | P03 | P08¦P09¦P10 | No | Low | High | No | Admin-level access to all platforms required within 2 business days of kickoff.
P08 | Integration / Celigo | Celigo flow — B2B identity sync (P21 → Shopify) | Sync P21 Company Profiles, Locations, and Customer-to-Company assignments into Shopify Plus via Celigo. | 36 | 0 | 36 | Celigo¦Shopify¦P21 | Data Sync | B2B, company sync, location sync, buyer identity, Celigo, P21, Shopify, customer assignment | Dev ops | Enterprise | 3 | High | Core | P07¦P03¦P02 | P25¦P26¦P28 | No | Medium | High | No | Client owns resolution of duplicate company/location records before sync. No custom P21 dev.
P09 | Integration / Celigo | Celigo flow — pricing & inventory sync (P21 → Shopify) | Synchronise pricing and inventory data from P21 to Shopify for purchasable SKUs. | 24 | 0 | 24 | Celigo¦Shopify¦P21 | Data Sync | pricing sync, inventory sync, SKU, P21, Celigo, Shopify, real-time | Dev ops | Mid-market¦Enterprise | 3 | High | Core | P07¦P03¦P02 | P25¦P26¦P27¦P28 | No | Medium | High | No | P21 must expose pricing and inventory endpoints. Real-time latency assumed acceptable.
P10 | Integration / Celigo | Celigo flow — order submission (Shopify → P21) | Push completed Shopify checkout orders to P21 to maintain ERP as operational truth. | 16 | 0 | 16 | Celigo¦Shopify¦P21 | Data Sync | order sync, order submission, checkout, P21, Celigo, ERP, Shopify | Dev ops | Mid-market¦Enterprise | 3 | Medium | Core | P07¦P03¦P02 |  | No | Medium | High | No | P21 order intake endpoint must be available. Returns/RMAs are out of scope.
P11 | PIM & Search | PIM product schema definition | Define scripts to merge fragmented product attribute data from legacy sources and P21 into the PIM schema. | 20 | 0 | 20 | PIM¦P21 | Data Modeling | PIM, product schema, attributes, data modeling, legacy mapping, P21, merge | Dev ops | Mid-market¦Enterprise | 2 | High | Core | P05 | P12¦P13¦P14 | No | Medium | Medium | No | Attribute mapping decisions owned by client; Codup implements once decisions are final.
P12 | PIM & Search | PIM initial ingestion flow (legacy attribute mapping) | Map and ingest existing Magento attributes into the PIM; tolerate imperfect data; includes CSV import. | 32 | 0 | 32 | PIM | Data Migration | PIM, Magento, attribute migration, ingestion, CSV import, legacy data, mapping | Dev ops | Mid-market¦Enterprise | 1 | High | Core | P11 | P13 | No | Medium | High | No | Magento attribute data must be exportable as CSV/JSON before ingestion begins. Simple products only.
P13 | PIM & Search | PIM data validation & cleansing scripts | Automated QA scripts to validate 90k normalised SKUs from Magento attribute families against PIM schemas. | 16 | 0 | 16 | PIM | Data Quality | PIM, validation, cleansing, QA, SKU, automated scripts, data quality | Dev ops | Mid-market¦Enterprise | 1 | High | Core | P12 | P14 | No | High | Medium | No | Manual data remediation is client-owned; scripts cover automated validation only.
P14 | PIM & Search | PIM data fetching & display integration | Integrate PIM attributes with Shopify/Celigo and P21 for consistent product data display on frontend. | 16 | 0 | 16 | PIM¦Shopify¦Celigo | Integration | PIM, product data, display, Shopify, integration, attributes | Dev ops | Mid-market¦Enterprise | 3 | High | Core | P13¦P11 | P27¦P30 | No | Medium | Medium | No | PIM schema must be finalised before this integration is built.
P15 | CMS & Content | Contentful content model definition | Define Contentful models for Pages, Blogs, and Resources with entry limits and linked references for editorial consistency. | 16 | 0 | 16 | Contentful | Content Modeling | Contentful, content model, pages, blogs, resources, editorial, CMS | Dev ops¦Marketing editor | SMB¦Mid-market¦Enterprise | 1 | None | Core | P01 | P16¦P17¦P18¦P19¦P20¦P21 | No | Medium | Low | No | Content types limited to those described. Additional types are a change request.
P16 | CMS & Content | Contentful Studio dynamic page rendering | Implement core React logic to iterate and render Contentful page slices/components from the Content Delivery API. | 12 | 12 | 24 | Contentful¦Vercel | Frontend Development | Contentful, Studio, page rendering, slices, components, React, CDA | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Core | P15¦P01 | P17¦P18¦P19¦P20 | No | Medium | Medium | No | Content model must be finalised before rendering logic is built.
P17 | CMS & Content | CMS component — hero banner (Contentful Studio slice) | Build hero banner as a constrained, reusable editorial slice within Contentful Studio/Experiences. | 8 | 12 | 20 | Contentful | Component Development | Contentful, hero banner, component, Studio, slice, CMS, editorial | Marketing editor | SMB¦Mid-market¦Enterprise | 1 | None | Core | P16 |  | Yes | High | Low | No | Contentful Studio must be licensed and provisioned. One slice component.
P18 | CMS & Content | CMS component — product grid/teaser (Contentful Studio slice) | Build product grid component allowing editors to feature Shopify-selected products via Contentful Studio. | 18 | 18 | 36 | Contentful¦Shopify | Component Development | Contentful, product grid, teaser, component, Studio, slice, Shopify, editorial | Marketing editor | SMB¦Mid-market¦Enterprise | 2 | None | Core | P16 |  | Yes | High | Medium | No | Shopify product data must be queryable from Contentful Studio.
P19 | CMS & Content | CMS component library expansion (8–10 opinionated components) | Develop 8–10 additional frontend-only components: Text Blocks, CTAs, Image Grids, Resource Cards. | 0 | 32 | 32 | Contentful | Component Development | CMS, components, text block, CTA, image grid, resource card, frontend, component library | Marketing editor | SMB¦Mid-market¦Enterprise | 1 | None | Core | P16 |  | Yes | High | Low | No | Scope fixed at 8–10 components. Expansion is a change request.
P20 | CMS & Content | Contentful Patterns / template pattern library | Configure Contentful Patterns to allow marketing to save and reuse page layouts and sections visually. | 0 | 18 | 18 | Contentful | Content Authoring | Contentful, patterns, templates, page layouts, reusable sections, marketing, CMS | Marketing editor | SMB¦Mid-market¦Enterprise | 1 | None | Core | P16 |  | Yes | High | Low | No | Requires Contentful Studio. Advanced editorial workflow features are excluded.
P21 | CMS & Content | Lead gen form — non-purchasable SKUs → Act-On | Build Show Interest form for non-purchasable SKUs; relay data to Act-On; noindex confirmation; auto-embed SKU. | 10 | 8 | 18 | Act-On¦Contentful | Lead Capture | lead gen, form, Act-On, non-purchasable, SKU, noindex, marketing automation | Marketing editor¦B2B buyer | SMB¦Mid-market¦Enterprise | 2 | None | Core | P06 |  | Yes | High | Low | No | Act-On credentials and form endpoint required. GDPR/consent copy is client-owned.
P22 | CMS & Content | Dynamic sitemap generation & robots control | Server-side logic to dynamically generate sitemaps for all product and content pages, respecting legacy URL structures. | 14 | 0 | 14 | Vercel | SEO | sitemap, robots.txt, SEO, server-side, dynamic, URL structure, legacy | Dev ops | SMB¦Mid-market¦Enterprise | 1 | High | Core |  |  | Yes | High | Low | No | Legacy URL structures must be documented before implementation.
P23 | CMS & Content | SEO — schema.org, breadcrumbs, semantic structure & noindex | Add schema.org markup (Org/Product/Breadcrumb); implement category breadcrumbs; ensure semantic headings; apply NoIndex rules. | 12 | 18 | 30 | Vercel¦Shopify | SEO | schema.org, breadcrumbs, semantic HTML, noindex, SEO, structured data, headings | Dev ops¦Marketing editor | SMB¦Mid-market¦Enterprise | 1 | None | Core |  |  | Yes | High | Low | No | NoIndex rules and breadcrumb taxonomy signed off by client before build.
P24 | CMS & Content | Edge middleware redirect service (90k+ redirects) | Custom edge middleware (Vercel Edge Config or equivalent) to serve 90k+ legacy redirects without performance impact. | 18 | 6 | 24 | Vercel | Infrastructure | redirects, edge middleware, Vercel, legacy URLs, SEO, 301, performance | Dev ops | Enterprise | 1 | High | Core | P02 |  | No | Medium | High | No | Redirect list must be provided as structured data. High data-volume preset — not applicable to SMB.
P25 | CMS & Content | URL mapping & validation script | Bulk script to map legacy Magento/ExpressionEngine URLs to new Next.js structure and validate path integrity. | 24 | 0 | 24 | Vercel | Data Migration | URL mapping, redirect, Magento, ExpressionEngine, Next.js, SEO, validation, legacy | Dev ops | Mid-market¦Enterprise | 1 | High | Core |  | P24 | No | High | Medium | No | Output is a validated mapping file. Legacy URL export required from client.
P26 | B2B | Shopify customer account auth flow | Configure and implement login, registration, and session management using Shopify native B2B authentication. | 14 | 8 | 22 | Shopify | Authentication | B2B, login, registration, session, authentication, Shopify, account | B2B buyer | Mid-market¦Enterprise | 1 | None | Core | P08 | P27¦P28¦P29¦P30¦P31 | No | Medium | Medium | No | Shopify Plus B2B plan must be provisioned and active.
P27 | B2B | Buyer identity enforcement at checkout | Apply selected company/location to checkout session; implement fallback rules when buyer identity is missing. | 12 | 8 | 20 | Shopify | Checkout | B2B, buyer identity, checkout, company, location, fallback, session | B2B buyer | Mid-market¦Enterprise | 2 | None | Core | P26¦P08 | P32¦P33¦P34¦P35 | No | Medium | High | No | Company/location sync must be live in Shopify before this can be tested.
P28 | B2B | Contextual pricing via @inContext GraphQL | Apply @inContext directive across all product queries to fetch B2B catalog prices from Shopify. | 16 | 8 | 24 | Shopify | Pricing | B2B, pricing, GraphQL, inContext, catalog, Shopify, contextual | B2B buyer | Mid-market¦Enterprise | 2 | None | Core | P09¦P08 | P29 | Yes | Medium | Medium | No | Shopify B2B catalogs must be configured per company/location before wiring.
P29 | B2B | Controlled pricing display feature toggle | Global toggle to show/hide B2B pricing; defaults to list price (safe default) when toggled off. | 12 | 12 | 24 | Shopify | Pricing | B2B, pricing toggle, list price, safe default, feature flag | Dev ops¦B2B buyer | Mid-market¦Enterprise | 1 | None | Core | P28 |  | Yes | Medium | Low | No | List price must be clearly identifiable in P21 source data.
P30 | B2B | Real-time inventory lookup (Shopify API) | Integrate PDP inventory display with Shopify API for low-latency real-time stock checks on purchasable SKUs. | 12 | 12 | 24 | Shopify¦P21 | Inventory | inventory, real-time, Shopify, API, PDP, stock, purchasable SKU | B2B buyer | Mid-market¦Enterprise | 2 | None | Core | P09¦P26 |  | Yes | Medium | Medium | No | P21 must respond within acceptable latency. Caching layer is a change request if needed.
P31 | B2B | Company location selector UI | UI for B2B users with multiple locations to select their operational context (buyer identity). | 16 | 8 | 24 | Shopify | UI Component | B2B, location selector, company, buyer identity, UI, multi-location | B2B buyer | Mid-market¦Enterprise | 1 | None | Core | P08¦P26 | P27 | Yes | High | Low | No | Location data must be synced to Shopify before end-to-end testing.
P32 | B2B | B2B cart logic extensions (quantity rules / volume pricing) | Enforce P21-defined quantity rules, increments, and volume price breaks in the headless cart UI. | 18 | 12 | 30 | Shopify¦P21 | Commerce Logic | B2B, cart, quantity rules, volume pricing, increments, headless, Shopify | B2B buyer | Mid-market¦Enterprise | 2 | None | Core | P09¦P27 |  | No | Medium | High | No | P21 rules must be synced to Shopify metafields before cart logic can be wired.
P33 | B2B | B2B account dashboard (P21 order history + documents) | Enhanced portal showing historical P21 orders (not just Shopify web orders) and B2B-specific documents. | 14 | 6 | 20 | Shopify¦P21 | Portal | B2B, account dashboard, order history, P21, documents, portal | B2B buyer | Enterprise | 2 | Medium | Enhancement | P26¦P02 |  | Yes | Medium | Medium | No | P21 order history API endpoint must be available and accessible.
P34 | Shopify / Ecommerce | Shopify payment provider config | Configure payment provider (e.g. Worldpay-compatible); test auth/capture/refund flows; validate B2B checkout behaviour. | 10 | 4 | 14 | Shopify | Payments | Shopify, payment, Worldpay, checkout, auth, capture, refund, B2B | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Core | P07 | P35 | No | Low | High | No | Sandbox credentials must be provided on day 1. Assumes Shopify hosted checkout.
P35 | Shopify / Ecommerce | Shopify shipping zones & carrier rates | Configure shipping zones/rules; connect carrier accounts; validate rate estimates at checkout. | 10 | 4 | 14 | Shopify | Shipping | Shopify, shipping, zones, carrier, rates, checkout, logistics | Dev ops | SMB¦Mid-market¦Enterprise | 2 | None | Core | P34 |  | Yes | Low | Low | No | Carrier API credentials must be available before work starts.
P36 | Shopify / Ecommerce | Shopify tax configuration | Configure tax behaviour including B2B exemptions; implement checkout messaging about customer-reported taxation. | 12 | 4 | 16 | Shopify | Tax | Shopify, tax, B2B, exemptions, checkout, compliance | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Core | P34 |  | Yes | Low | Medium | No | Tax rules and exemption logic must be signed off by client before implementation.
P37 | Shopify / Ecommerce | Google Merchant Center (GMC) feed setup | Map required fields (price, inventory, images, brand) to Shopify metafields; configure GMC feed; validate daily updates. | 8 | 4 | 12 | Shopify | Marketing / Feeds | GMC, Google Merchant Center, product feed, Shopify, metafields, inventory, daily sync | Marketing editor | SMB¦Mid-market¦Enterprise | 1 | High | Enhancement | P09 |  | Yes | High | Low | No | GMC account access required. Feed validated against live SKUs.
P38 | Shopify / Ecommerce | Shopify checkout settings (account-required + branding) | Configure account-required checkout, branding tokens, and policies. No custom logic. | 6 | 4 | 10 | Shopify | Checkout | Shopify, checkout, branding, account required, policies, settings | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Core | P34 | P27¦P39¦P40 | No | Low | Low | No | Scoped to Shopify native settings only. Deep checkout logic is out of scope.
P39 | Shopify / Ecommerce | Headless cart → Shopify checkout handoff | Implement session handoff from headless cart to Shopify checkout; handle error states and return routing. | 20 | 8 | 28 | Shopify¦Vercel | Checkout | headless, cart, checkout handoff, session, Shopify, error handling, return routing | Dev ops | Mid-market¦Enterprise | 2 | None | Core | P38 | P40 | No | Medium | High | No | Assumes headless cart is already built; this is the bridge layer only.
P40 | Shopify / Ecommerce | Checkout UI extensions (PO/reference fields + messaging) | Build Shopify checkout UI extensions for PO/reference number input, required fields, and messaging blocks. | 20 | 8 | 28 | Shopify | Checkout | checkout extensions, PO number, reference fields, messaging, Shopify, B2B, UI extension | B2B buyer¦Dev ops | Mid-market¦Enterprise | 1 | None | Enhancement | P39 |  | Yes | Medium | Medium | No | Shopify Plus required. Extensions limited to Shopify extension points.
P41 | PIM & Search | Klevu indexing integration (PIM + Contentful) | Build export mechanism combining PIM product attributes and Contentful non-product content for Klevu search indexing. | 12 | 0 | 12 | Klevu¦PIM¦Contentful | Search | Klevu, search, indexing, PIM, Contentful, product, content, export | Dev ops | Mid-market¦Enterprise | 3 | High | Core | P04¦P13¦P15 | P42¦P43 | No | Medium | Medium | No | Klevu subscription must cover 90k+ SKUs plus content. Indexing must be live before PLP.
P42 | PIM & Search | Faceted filtering / PLP interface (Klevu-powered) | Implement Product Listing Page UI with category filters, sorting, and faceted search wired to Klevu API results. | 18 | 12 | 30 | Klevu¦Shopify | Search UI | PLP, product listing, facets, filters, sorting, Klevu, search, category | B2B buyer | Mid-market¦Enterprise | 2 | High | Core | P41 |  | Yes | High | Medium | No | Klevu must be indexed before PLP can be tested. Facet taxonomy signed off before build.
P43 | PIM & Search | Sitewide search — autocomplete, results page & layout | Implement search box, autocomplete/suggestions, and results page; layout via Contentful Studio; wired to Klevu. | 18 | 16 | 34 | Klevu¦Contentful | Search UI | search, autocomplete, suggestions, results page, Klevu, Contentful, sitewide | B2B buyer¦Marketing editor | Mid-market¦Enterprise | 2 | None | Enhancement | P41¦P15 |  | Yes | High | Medium | No | Klevu indexing must be live. Content layout models must be finalised in Contentful first.
P44 | CMS & Content | SSR / static generation & Core Web Vitals optimisation | Configure Next.js SSR or static generation for critical pages; ensure Core Web Vitals compliance. | 0 | 16 | 16 | Vercel | Performance | SSR, static generation, Next.js, Core Web Vitals, performance, SEO, Vercel | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Enhancement | P16 |  | Yes | High | Low | No | Framework must be Next.js. Deep infra changes outside Next.js config are out of scope.
P45 | CMS & Content | Accessibility implementation (keyboard nav, contrast, focus states) | Implement keyboard navigation, colour contrast, font sizes, focus/active states to WCAG template-level compliance. | 0 | 20 | 20 | Vercel | Accessibility | WCAG, accessibility, keyboard navigation, focus states, colour contrast, a11y | Dev ops | SMB¦Mid-market¦Enterprise | 1 | None | Enhancement | P19 |  | Yes | Medium | Low | No | Template/component-level only. Formal external audit is excluded.
TOTAL — ALL PRESETS |  |  |  | 654 | 310 | 964

## 📖 Data Dictionary
DATA DICTIONARY — COLUMN REFERENCE
Column name | Group | Purpose | Allowed values / format
ID | Core | Unique preset identifier for cross-referencing Requires/Blocks columns. | P01 – P99 (increment as you add presets)
Category | Core | High-level domain grouping for browsing and summary roll-ups. | Shopify / Ecommerce ¦ B2B ¦ CMS & Content ¦ Integration / Celigo ¦ PIM & Search ¦ Dev Environment
Preset Name | Core | Short, reusable name. Should be self-explanatory with no project-specific context. | Free text, max 60 chars. No client names.
Description | Core | One-sentence scope statement. What does this preset cover and what does it explicitly exclude? | Free text. Keep to 1–2 sentences.
BE (h) | Core | Estimated backend hours at base complexity. Blue = hardcoded input, adjust per project. | Integer hours
FE (h) | Core | Estimated frontend hours at base complexity. Blue = hardcoded input, adjust per project. | Integer hours
Total (h) | Core | Auto-calculated: BE + FE. Do not edit. | Formula =E+F
Platforms | Discoverability | Which third-party platforms does this preset directly touch? | Pipe-separated: Shopify ¦ Celigo ¦ Contentful ¦ Klevu ¦ P21 ¦ Act-On ¦ Vercel ¦ PIM
Req. type | Discoverability | Functional category — used to match a client requirement to a preset class. | Authentication ¦ Checkout ¦ Commerce Logic ¦ Component Development ¦ Content Authoring ¦ Content Modeling ¦ Data Migration ¦ Data Modeling ¦ Data Quality ¦ Data Sync ¦ Frontend Development ¦ Infrastructure ¦ Integration ¦ Inventory ¦ Lead Capture ¦ Marketing / Feeds ¦ Payments ¦ Performance ¦ Pricing ¦ Portal ¦ Research & Discovery ¦ SEO ¦ Search ¦ Search UI ¦ Shipping ¦ Tax ¦ UI Component
Keywords | Discoverability | Free-text searchable tags. Use CTRL+F in Excel or FILTER() to search. | Comma-separated, lowercase, no quotes
User story tags | Discoverability | Who is the end beneficiary of this preset? | Pipe-separated: B2B buyer ¦ Dev ops ¦ Marketing editor
Project size fit | Complexity | Which project sizes is this preset appropriate for? Helps exclude irrelevant presets from small projects. | Pipe-separated: SMB ¦ Mid-market ¦ Enterprise
Integration count | Complexity | How many distinct platform connections does this preset assume? Use to estimate integration complexity. | Integer 1–5
Data volume | Complexity | Does this preset's scope or risk change significantly with high data volume (e.g. 90k SKUs, 90k redirects)? | None ¦ Low ¦ High
Phase | Sequencing | When in a project lifecycle does this preset typically land? | Foundation (env setup, R&D spikes) ¦ Core (main build) ¦ Enhancement (optimisation, extras)
Requires | Sequencing | Preset IDs that must be completed before this preset can begin. Pipe-separated. | Pipe-separated preset IDs, e.g. P07¦P08. Leave blank if none.
Blocks | Sequencing | Preset IDs that cannot begin until this preset is done. Pipe-separated. | Pipe-separated preset IDs. Leave blank if none.
Can parallel | Sequencing | Can this preset run concurrently with other work, or does it have hard serial dependencies? | Yes ¦ No
AI assist | Effort intelligence | How much do AI coding tools (Cursor, Copilot, etc.) compress this preset's effort? | Low (minimal gain, e.g. complex integration logic) ¦ Medium ¦ High (boilerplate, components, scripts)
Risk | Effort intelligence | Likelihood that this preset will exceed estimate due to external dependencies, unknowns, or complexity. | Low ¦ Medium ¦ High
Research needed | Effort intelligence | Is a separate R&D spike required before this preset can be accurately estimated or begun? | Yes ¦ No
Notes / Assumptions | Notes | Key assumption that, if violated, makes this preset a change request. One sentence. | Free text

## 🔍 Query Examples
QUERY TEMPLATES — COPY THESE FORMULAS INTO MASTER DATABASE SHEET TO FILTER
Query intent | Formula (paste into a new sheet, referencing 📋 Master Database)
All Enterprise-fit presets | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("Enterprise",'📋 Master Database'!L4:L48)))
All Shopify-touching presets | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("Shopify",'📋 Master Database'!H4:H48)))
All Celigo flows | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("Celigo",'📋 Master Database'!H4:H48)))
All Foundation-phase presets | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!O4:O48="Foundation")
All Core-phase presets | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!O4:O48="Core")
All Enhancement-phase presets | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!O4:O48="Enhancement")
High-risk presets only | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!T4:T48="High")
Low-risk presets only | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!T4:T48="Low")
Presets where AI saves most time (High assist) | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!S4:S48="High")
Presets that can run in parallel | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!R4:R48="Yes")
High data-volume presets (flag for large catalogs) | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!N4:N48="High")
B2B buyer-facing presets | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("B2B buyer",'📋 Master Database'!K4:K48)))
Marketing editor-facing presets | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("Marketing editor",'📋 Master Database'!K4:K48)))
R&D spikes only | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!U4:U48="Yes")
Presets needing >20h BE | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!E4:E48>20)
Search for keyword (edit SEARCH term in formula) | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("klevu",'📋 Master Database'!J4:J48)))
Shopify B2B full build (Shopify + B2B category) | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("Shopify",'📋 Master Database'!H4:H48)) * ('📋 Master Database'!B4:B48="B2B"))
SMB-appropriate presets only | =FILTER('📋 Master Database'!A4:V48, ISNUMBER(SEARCH("SMB",'📋 Master Database'!L4:L48)))
Checkout-type requirements | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!I4:I48="Checkout")
All SEO-type requirements | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!I4:I48="SEO")
Multi-platform presets (integration count >= 3) | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!M4:M48>=3)
No-spike presets (can estimate without R&D) | =FILTER('📋 Master Database'!A4:V48, '📋 Master Database'!U4:U48="No")